## Sheet1
Sr.no | Jira Ticket No. | Object | Issue Description | Raised By | Assigned To | Priority | Remarks | Status
1 | AXCELEFT-3250 | IW32 | Tech-AXCELEFT_1471-IW32-Runtime error during TECO of the workorder | Manoj San | Vikas San | Low | 7/16/2026 Manoj San | Closed
Encountered runtime error when TECO work order in transaction IW32
2 | AXCELEFT-3252 | ME59N | ABAP Dump - P2P-0030-100 - ME59N - User unable to create PO and getting ABAP dump - | Sankar San | Vikas San | Medium | 16/07 - Raise by Sankar San | Pending Functional testing
20/07 - Vikas San looking into it
3 | AXCELEFT-3245 | /CCEJ/RURCO_FI_UPLD | /CCEJ/RURCO_FI_UPLD - Error during conversion - field type conflict | Ravish San | Vikas San | Medium | 17/07 - Raise by Ravish San | Pending Functional testing
20/07 - Vikas San looking into it
4 | AXCELEFT-3368 | ? | ABAP Dump - P2P-0030-160 - MEMASSPO - User unable to change the POs in mass and get... | Sankar San | Vikas San | Medium | 17/07 - Raise by Ravish San | Pending Functional testing
20/07 - Vikas San looking into it
5 | AXCELEFT-3369 | ME58 | ABAP Dump - P2P-0030-100 - ME58 - User unable to create PO from PR and getting ABAP... | Sankar San | Vikas San | Medium | 17/07 - Raise by Ravish San | Pending Functional testing
20/07 - Vikas San looking into it
6 | AXCELEFT-3370 | ME21N | ABAP Dump - P2P-0040-010 - ME21N - User unable to create PO and getting ABAP dump -... | Sankar San | Vikas San | Medium | 17/07 - Raise by Ravish San | Pending Functional testi
20/07 - Vikas San looking into it